## Product Backlog
Product Backlog: Feline Friendship Force
SPRINT
ID | Description | 1 | 2 | 3 | 4 | 5
| Hours Needed per Sprint | 30 | 70.25 | 199.5 | 108.25 | 27.75
1 | Production | 4
2 | Epic: As the player, I want to know the conditions of winning and losing. COS: Levels have win and lose screens. COS: HUD shows victory condition for level. COS: Intro levels explain the rules. | 10.5
3 | Epic: As the player, I want to know how movement works. COS: Highlight cats for selection. COS: When cat is selected, highlight selectable nodes. COS: Dog footprints to show its patrol path. COS: Dog notice effect when it sees a cat. | 15.5
Sprint 1↑ | Proof of Concept Gameplay ↑ 10/16/17
1 | Production |  | 39.75
4 | Epic: As the player, I want to feel like I want to beat the game. COS: Test if puzzles are fun. COS: Test if puzzles are complex. COS: Test puzzles for conveyance. |  | 13
5 | Epic: As the player, I want to feel like I'm outsmarting the game. COS: Create an end for the game. COS: Make sure all levels are completed. COS: Make sure all UI elements are polished. COS: Give players a reason to continue playing. |  | 17.5
Sprint 2↑ | Vertical Slice ↑ 10/23/17
1 | Production |  |  | 47.5
6 | Epic: As the player, I want the game to be more interesting. COS: Add juice to UI. COS: Add animations, sounds and fonts to the game. COS: Add box, cat nip and bone features to levels. |  |  | 57
7 | Epic: As the player, I want to know how the dog AI works. COS: The dog notice effect appears when it sees a cat. COS: Place dog paw prints to show AI patrol path. COS: Display which cat the dog is chasing after. |  |  | 39.5
8 | Epic: As the player, I want to know what is interactable in the game. COS: Place a shader on each cat. COS: Make pressure plate display water flowing out of water hose. COS: Test dog having the first turn. COS: Add finger swiping to interact with UI tutorial. |  |  | 55.5
Sprint 3↑ | Alpha ↑ 11/6/17
1 | Production |  |  |  | 76
9 | Epic: As the player, I want a reason to buy the game. COS: Create a good marketing campaign. COS: Make the game look appealing. |  |  |  | 15.75
10 | Epic: As the player, I want to feel rewarded. COS: Add particle systems to the win screen. COS: Add barking and sniffing sounds to dog. COS: Add sounds to collecting cat nip and entering box. |  |  |  | 16.5
Sprint 4↑ | Beta ↑ 11/20/17
1 | Production |  |  |  |  | 18.75
11 | Epic: As the developer, I want to make sure all documentation is finished. COS: Make sure the GDD is fully documented and well structured. COS: Create and publish a wiki for the game. |  |  |  |  | 3
12 | Epic: As the stakeholder, I want to launch the game. COS: Everything is optimized for submission to Android Store. |  |  |  |  | 6
Sprint 5↑ | Launch ↑ 11/27/17
| Hours Needed as a Whole | 435.75 | 405.75 | 335.5 | 136 | 27.75

## POCG
Sprint Backlog: Proof of Concept Gameplay |  |  |  |  | Days in Sprint |  |  |  |  | Acceptable Havoc
[5 empty] | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Role | Name | Initals | Total Hours
ID | Epic Actual Hours | Epic/Tasks | Task Actual Hours | Initials | [5 empty] | Artist | Brennen Dumas | BD | 6.5
1 | 4 | Production | [7 empty] | Programmer | Rui Xie | RX | 12
|  | Daily Standup | 3 | All |  |  | 1 | 1 | 1 | Level Designer | Dominique Stafford | DS | 8
|  | Stakeholder meeting | 1 | All |  |  |  | 1 |  | Level Designer | Chris Wysocki | CW | 9.5
|  | Update GDD | 0.5 | BD |  | 0.5
|  | Update GDD | 2.5 | DS |  | 1 |  | 1.5
|  | Quality check for all submission requirements | 1 | CW |  |  |  |  | 1
2 | 10.5 | Epic: As the player, I want to know the conditions of winning and losing. COS: Levels have win and lose screens. COS: HUD shows victory condition for level. COS: Intro levels explain the rules.
|  | Added fade screen between levels | 0.5 | RX |  | 0.5
|  | Speed paper prototyping for new levels and mechanics | 1 | DS |  |  | 0.5 | 0.5
|  | Build levels in Unity | 1 | DS |  |  | 0.5 | 0.5
|  | Playtest Build | 1 | DS |  |  |  | 1 | 1
|  | Speed paper prototyping for new levels and mechanics | 0.5 | CW |  |  | 0.5
|  | Make initial UI and HUD elements in the game | 3.5 | CW |  |  | 1 | 2.5
|  | Make level template with screen & control requirements | 1.5 | CW |  |  |  |  | 1.5
|  | Build levels in Unity | 1.5 | CW |  |  | 1 |  | 0.5
|  | Playtest Build | 0.5 | CW |  |  |  |  | 0.5
3 | 15.5 | Epic: As the player, I want to know how movement works. COS: Highlight cats for selection. COS: When cat is selected, highlight selectable nodes. COS: Dog footprints to show its patrol path. COS: Dog notice effect when it sees a cat.
|  | Create exclamation point for dog notice effect. | 0.5 | BD |  |  |  | 0.5
|  | Create paw prints to show dog paths | 0.5 | BD |  |  | 0.5
|  | Create Idle animation for the cat. | 2.5 | BD |  | 2.5
|  | Create initial design for the dog. | 1.5 | BD | 1.5
|  | Refactor Current Scripts | 2 | RX | 1 | 0.5 |  |  | 0.5
|  | Review State Machine to create pluggable AI systemfor dogs | 0.5 | RX | 0.5
|  | Bug fix and code optimization | 3.5 | RX |  | 1.5 |  | 1.5 | 0.5
|  | Setup P4 and make POCG Build | 1.5 | RX | 0.5 |  |  |  | 1
|  | Re-working Dog AI chasing and patrol script | 3 | RX |  |  | 2 | 1
|  | Search for sound in the SMU sound library | 1.5 | DS |  |  | 0.5 | 1

## VS
Sprint Backlog: Vertical Slice |  |  |  |  | Days in Sprint |  |  |  |  | Acceptable Havoc
[5 empty] | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Role | Name | Initals | Total Hours
ID | Epic Actual Hours | Epic/Tasks | Task Actual Hours | Initials | [5 empty] | Artist | Brennen Dumas | BD | 16.75
1 | 39.75 | Production | [7 empty] | Programmer | Ashley Pancho | AP | 12 | Ashley joined on day 2
|  | Daily Standup | 5 | All |  | 1.25 | 1.25 | 1.25 | 1.25 | Programmer | Rui Xie | RX | 15.5
|  | Retrospective/Kleenex tessting/Sprint Planning | 12 | All | 12 |  |  |  |  | Level Designer | Dominique Stafford | DS | 13.75
|  | Add Ashley (new programmer) to team and moved rooms | 2.5 | All |  | 2.5 |  |  |  | Level Designer | Chris Wysocki | CW | 15.25
|  | Intigrating all elements for final build sprint | 10 | All |  |  |  |  | 10
|  | Updating GDD | 0.25 | BD |  |  |  | 0.25
|  | Catching up on state of project | 2 | AP |  | 2
|  | Troubleshooting final build sprint for submission | 1 | AP |  |  |  |  | 1
|  | Catching Ashley up on state of project | 1 | RX |  | 1
|  | Troubleshooting final build sprint for submission | 1 | RX |  |  |  |  | 1
|  | Updating GDD | 1 | DS |  |  | 1
|  | Level design meeting to discuss what is working in the game | 1.5 | DS |  | 1.5
|  | Level design meeting to discuss what is working in the game | 1.5 | CW |  | 1.5
|  | Troubleshooting final build sprint for submission | 1 | CW |  |  |  |  | 1
4 | 13 | Epic: As the player, I want to feel like I want to beat the game. COS: Test if puzzles are fun. COS: Test if puzzles are complex. COS: Test puzzles for conveyance.
|  | Create a simple water hose for puzzle use | 1 | BD |  |  |  |  | 1
|  | Add sounds to game | 2 | AP |  |  |  | 2
|  | Added Dog notice animation | 1 | RX |  |  |  | 1
|  | Add shader effects | 1 | RX |  |  | 1
|  | Search SMU sound library | 0.5 | DS |  |  | 0.5
|  | Make Unity levels | 3.25 | DS |  | 1.5 | 1.75
|  | Playtest Build | 1 | DS |  |  |  |  | 1
|  | Make Unity levels | 1.25 | CW |  |  |  | 1.25
|  | Playtest Build | 2 | CW |  |  | 1 | 1
|  | Search SMU sound library | 1.5 | CW |  |  | 1.5
5 | 17.5 | Epic: As the player, I want to feel like I'm outsmarting the game. COS: Create an end for the game. COS: Make sure all levels are completed. COS: Make sure all UI elements are polished. COS: Give players a reason to continue playing.
|  | Create animation sprite sheet for dog sideways movement | 1.5 | BD |  |  | 1 | 0.5
|  | Animate cat for moving upward | 3 | BD |  | 1 | 2
|  | Animate cat for downward movement | 2 | BD |  |  | 2
|  | Create general layouts for menus | 0.5 | BD |  | 0.5
|  | Create art for UI buttons | 2 | BD |  | 2
|  | Make sure enemy dogs don't move to the same spot | 1 | AP |  |  | 1
|  | Write code to allow for multiple enemies in a level | 1.5 | AP |  |  | 1.5
|  | Debug level template scene | 1 | AP |  |  |  | 1
|  | Code and animation for the box | 1 | RX |  | 1
|  | Set up cat animations in Unity | 1 | RX |  |  |  | 1
|  | Add box close animations when cat leaves | 0.5 | RX |  |  |  | 0.5
|  | Bug fixing and code optimization | 2.5 | RX |  | 0.5 | 0.5 | 1.5
|  | Intigrating art and creating a Unity prefab for the art | 1.5 | CW |  |  |  | 1.5

## Alpha
Sprint Backlog: Alpha |  |  |  |  | Days in Sprint | [9 empty] | Acceptable Havoc
[5 empty] | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Role | Name | Initals | Total Hours
ID | Epic Actual Hours | Epic/Tasks | Task Actual Hours | Initials | [10 empty] | Artist | Brennen Dumas | BD | 30 | bar: Days in Sprint Day 1
1 | 47.5 | Production | [12 empty] | Programmer | Ashley Pancho | AP | 30
|  | Daily Standup | 17.5 | All |  | 1.25 | 2.5 | 1.25 | 1.25 | 1.25 | 2.5 | 2.5 | 2.5 | 2.5 | Programmer | Rui Xie | RX | 30
|  | Retrospective/Klenex testing/Planning | 15 | All | Days in Sprint Day 1: 15 | Level Designer | Dominique Stafford | DS | 30
|  | Intigrating all elemnts for final sprint build | 10 | All | Days in Sprint Day 10: 10 | Level Designer | Chris Wysocki | CW | 30
|  | Starting to convert GDD to Wiki | 1 | AP | bar: Days in Sprint Day 9
|  | Updating GDD | 3.5 | DS | Days in Sprint Day 5: 2; Days in Sprint Day 7: 1; Days in Sprint Day 9: 0.5
|  | Updating GDD | 0.5 | CW | Days in Sprint Day 8: 0.5
6 | 57 | Epic: As the player, I want the game to be more interesting. COS: Add juice to UI. COS: Add animations, sounds and fonts to the game. COS: Add box, cat nip and bone features to levels.
|  | Create animation for the idle dog. | 1 | BD | bar: Days in Sprint Day 2
|  | Concept out new art assets for overall design change | 1 | BD | bar: Days in Sprint Day 2
|  | Model background assets for new background sprites | 2.5 | BD | Days in Sprint Day 3: 2.5
|  | Texture assets for level population | 2.5 | BD | Days in Sprint Day 4: 2.5
|  | Texture background elements | 1.5 | BD | Days in Sprint Day 5: 1.5
|  | Sculpt the cat model for player use | 3 | BD | Days in Sprint Day 6: 3
|  | UV cat model for texturing | 1 | BD | bar: Days in Sprint Day 7
|  | Texture cat model / render for sprite | 3 | BD | Days in Sprint Day 7: 3
|  | Sculpt the dog model for enemy AI | 2 | BD | Days in Sprint Day 8: 2
|  | UV dog model for texturing | 1 | BD | bar: Days in Sprint Day 8
|  | Texture dog model / render for sprite | 3 | BD | Days in Sprint Day 9: 3
|  | Proofread game text | 1 | AP | bar: Days in Sprint Day 2
|  | Feature polish existing elements | 1.5 | AP | Days in Sprint Day 2: 1.5
|  | Add splash screen to game | 1 | AP | bar: Days in Sprint Day 3
|  | Polish game sounds | 1 | AP | bar: Days in Sprint Day 3
|  | Implement achievement system backend | 2.5 | AP | Days in Sprint Day 4: 2.5
|  | Bug fixing | 2.5 | AP | Days in Sprint Day 5: 2.5
|  | Add juice to sprites | 2.5 | AP | Days in Sprint Day 6: 2.5
|  | Add juice to win and loss screens | 2.5 | AP | Days in Sprint Day 7: 2.5
|  | Optimize for tablet | 3.5 | AP | Days in Sprint Day 8: 2; Days in Sprint Day 9: 1.5
|  | Playtesting with new challenge elements | 2.5 | AP | Days in Sprint Day 9: 1.5; Days in Sprint Day 10: 1
|  | Add juice to winscreen | 2.25 | RX | Days in Sprint Day 8: 1.75; Days in Sprint Day 9: 0.5
|  | Add save feature to achievement system | 2.75 | RX | Days in Sprint Day 4: 2; Days in Sprint Day 9: 0.75
|  | Add wishlist items (catnip and save states) to game | 0 | RX
|  | Build Unity Levels | 4.5 | DS | Days in Sprint Day 8: 2.5; Days in Sprint Day 9: 2
|  | Build Unity Levels/incorpporate new puzzle features | 5.5 | CW | Days in Sprint Day 3: 2; Days in Sprint Day 4: 1; Days in Sprint Day 5: 1; Days in Sprint Day 8: 1.5
7 | 39.5 | Epic: As the player, I want to know how the dog AI works. COS: The dog notice effect appears when it sees a cat. COS: Place dog paw prints to show AI patrol path. COS: Display which cat the dog is chasing after.
|  | Add multiple enemy AI elements to game | 2 | RX | Days in Sprint Day 2: 2
|  | Experimenting with new AI systems | 1.5 | RX | Days in Sprint Day 3: 1.5
|  | Bug fix | 4 | RX | bar: Days in Sprint Day 2 to Days in Sprint Day 3; Days in Sprint Day 5 to Days in Sprint Day 6
|  | Playtest the game (focus on how people handle the dog) | 3 | RX | Days in Sprint Day 7: 2; Days in Sprint Day 10: 1
|  | Iteratie from playtest feedback | 3 | RX | bar: Days in Sprint Day 8 to Days in Sprint Day 10
|  | Iterate from playtest feedback | 5.5 | DS | Days in Sprint Day 4: 2.75; Days in Sprint Day 7: 1.5; Days in Sprint Day 9: 1.25
|  | Playtest the game (focus on how people handle the dog) | 8 | DS | Days in Sprint Day 2: 2.5; Days in Sprint Day 3: 0.75; Days in Sprint Day 5: 1.5; Days in Sprint Day 6: 2.75; Days in Sprint Day 10: 0.5
|  | Iterate from playtest feedback | 4.25 | CW | Days in Sprint Day 4: 2.25; Days in Sprint Day 5: 1; Days in Sprint Day 8: 1
|  | Playtest the game (focus on how people handle the dog) | 8.25 | CW | Days in Sprint Day 2: 2.5; Days in Sprint Day 5: 1; Days in Sprint Day 6: 2; Days in Sprint Day 7: 2; Days in Sprint Day 9: 0.75
8 | 55.5 | Epic: As the player, I want to know what is interactable in the game. COS: Place a shader on each cat. COS: Make pressure plate display water flowing out of water hose. COS: Test dog having the first turn. COS: Add finger swiping to interact with UI tutorial.
|  | Fix node selection | 0.75 | RX | Days in Sprint Day 7: 0.75
|  | Add re-pick node feature | 0.75 | RX | Days in Sprint Day 8: 0.75
|  | Make water animator in Unity | 1 | RX | bar: Days in Sprint Day 5
|  | Fix turn counter conveyance based on feedback | 0.5 | RX | Days in Sprint Day 9: 0.5
|  | Update the art and double check element layers | 2 | CW | bar: Days in Sprint Day 9 to Days in Sprint Day 10
|  | Replace water sprite with particle effect system | 1 | CW | bar: Days in Sprint Day 4

## Beta
Sprint Backlog: Beta |  |  |  |  | Days in Sprint | [9 empty] | Acceptable Havoc
[5 empty] | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Role | Name | Initals | Total Hours
ID | Epic Actual Hours | Epic/Tasks | Task Actual Hours | Initials | [10 empty] | Artist | Brennen Dumas | BD | 19.75 | Missed Days | bar: Days in Sprint Day 1
1 | 76 | Production | [12 empty] | Programmer | Ashley Pancho | AP | 23.25
|  | Daily Standup | 10.75 | All |  | 1.25 | 1.25 | 1.25 | 1.25 |  | 2.5 | 1.25 | 1 | 1 | Programmer | Rui Xie | RX | 22.5
|  | Sprint retrospective/Klenix testing/Planning for next sprint | 15 | All | Days in Sprint Day 1: 15 | Level Designer | Dominique Stafford | DS | 24
|  | Beta play testing at SMU main campus | 12 | All | Days in Sprint Day 6: 12 | Level Designer | Chris Wysocki | CW | 23.75 | Missed Day
|  | Intigrating all elemnts for final sprint build | 12 | All | Days in Sprint Day 10: 12
|  | Updating GDD | 1.5 | AP | Days in Sprint Day 4: 0.5; Days in Sprint Day 8: 1
|  | Creating usability survey for beta play testing | 2.25 | AP | Days in Sprint Day 4: 1.5; Days in Sprint Day 5: 0.75
|  | Writing up the usability report | 2.5 | AP | Days in Sprint Day 7: 2.5
|  | Updating GDD | 2.75 | RX | Days in Sprint Day 4: 0.75; Days in Sprint Day 8: 1; Days in Sprint Day 9: 1
|  | Writing up the usability report | 0.5 | RX | Days in Sprint Day 7: 0.5
|  | Updating GDD | 2.75 | DS | Days in Sprint Day 8: 1; Days in Sprint Day 9: 1.75
|  | Writing up the usability report | 3.5 | DS | Days in Sprint Day 7: 0.5; Days in Sprint Day 8: 3
|  | Updating GDD | 2.75 | CW | Days in Sprint Day 8: 1; Days in Sprint Day 9: 1.75
|  | Creating usability survey for beta play testing | 2.25 | CW | Days in Sprint Day 4: 1.5; Days in Sprint Day 5: 0.75
|  | Writing up the usability report | 5.5 | CW | Days in Sprint Day 7: 2.5; Days in Sprint Day 8: 3
9 | 15.75 | Epic: As the player, I want a reason to buy the game. COS: Create a good marketing campaign. COS: Make the game look appealing.
|  | Work on model perspectives for better look | 7 | BD | Days in Sprint Day 2: 1.25; Days in Sprint Day 3: 3; Days in Sprint Day 4: 1; Days in Sprint Day 5: 1.75
|  | Work on level layouts | 2 | BD | Days in Sprint Day 7: 2
|  | Finish art for posters and advertising | 3 | BD | Days in Sprint Day 8: 3
|  | Reword UI text from playtesting feedback | 0.75 | AP | Days in Sprint Day 5: 0.75
|  | Make trailer for the game | 3 | DS | Days in Sprint Day 7: 1.25; Days in Sprint Day 8: 1.75
10 | 16.5 | Epic: As the player, I want to feel rewarded. COS: Add particle systems to the win screen. COS: Add barking and sniffing sounds to dog. COS: Add sounds to collecting cat nip and entering box.
|  | Add more conveyance though sound | 1.75 | AP | Days in Sprint Day 2: 1.75
|  | Bug fixing UI | 0.75 | AP | Days in Sprint Day 3: 0.75
|  | Iteration from feedback for UI and Sound | 2.5 | AP | Days in Sprint Day 4: 1.25; Days in Sprint Day 7: 0.5; Days in Sprint Day 8: 0.25; Days in Sprint Day 9: 0.5
|  | Make dog animator face the cat it is chasing | 1 | RX | bar: Days in Sprint Day 4
|  | Add particle effect system to win screen | 1.5 | RX | Days in Sprint Day 2: 1.5
|  | Bug Fix and code optimization | 5.5 | RX | Days in Sprint Day 3: 1.5; Days in Sprint Day 5: 1; Days in Sprint Day 6: 1; Days in Sprint Day 7: 1; Days in Sprint Day 8: 1
|  | Playtest and QA | 2.75 | DS | Days in Sprint Day 2: 1.25; Days in Sprint Day 3: 1; Days in Sprint Day 8: 0.5
|  | Proofreading Game Text | 0.75 | DS | Days in Sprint Day 5: 0.75
|  | Search for new sounds for the dog and box | 1 | CW | bar: Days in Sprint Day 2
|  | Update in-level art and ensure all layers are correct | 2 | CW | Days in Sprint Day 5: 2
|  | QA and playtest the current build | 2 | CW | bar: Days in Sprint Day 2; Days in Sprint Day 4

## Launch
Sprint Backlog: Launch |  |  |  |  | Days in Sprint |  |  | Acceptable Havoc
[5 empty] | Day 1 | Day 2 | Day 3 | Role | Name | Initals | Total Hours
ID | Epic Actual Hours | Epic/Tasks | Task Actual Hours | Initials |  |  |  | Artist | Brennen Dumas | BD | 5.25
1 | 18.75 | Production | [5 empty] | Programmer | Ashley Pancho | AP | 5.75
|  | Daily Standup | 1.25 | All |  | 1.25 |  | Programmer | Rui Xie | RX | 5.25
|  | Kleenex Testing and Retrospective | 15 | All | 15 |  |  | Level Designer | Dominique Stafford | DS | 5.25
|  | Worked on Developer Wiki | 1.5 | AP |  | 1.5 |  | Level Designer | Chris Wysocki | CW | 6.25
|  | Worked on GDD | 1 | AP |  | 1
11 | 3 | Epic: As the developer, I want to make sure all documentation is finished. COS: Make sure the GDD is fully documented and well structured. COS: Create and publish a wiki for the game.
|  | Work on marketing materials for wiki (icons/Header) | 1.5 | BD |  | 1.5
|  | Print art for DVD case/disk | 0.5 | BD |  | 0.5
|  | Finialized and submitied all marketing and game materials | 1 | CW |  |  | 1
12 | 6 | Epic: As the stakeholder, I want to launch the game. COS: Everything is optimized for submission to Android Store.
|  | Make the launch build | 0.5 | RX |  |  | 0.5
|  | Iteration from playtest | 0.5 | RX |  | 0.5
|  | Optomizing code for Launch | 1 | RX |  | 1
|  | QA and Playtest final Build | 2 | DS |  | 2
|  | QA and Playtest final Build | 2 | CW |  | 2