## FFF QA Database
Guildhall JIRA
Displaying 18 issues at 01/Dec/17 9:58 AM.
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Creator | Created | Last Viewed | Updated | Resolved | Time Spent | Description | Progress | Σ Progress | Σ Time Spent | Σ Remaining Estimate | Σ Original Estimate | Labels
TGP1 Bug Database Team C27.14 | TGP1BC2714-1 | Cat sometimes doesn't go into box when selected. | Bug | Done | Lowest | Done | Dominique S. | Dominique S. | Dominique S. | 2017-11-07 11:45 | 2017-12-01 09:57 | 2017-11-30 22:04 | 2017-11-07 12:20 | 300 | The cat at times doesn't go into the box immediately and requires another finger tap. | 100% | 100% | 300 | 0 | 0 | Bugs, SD-Design, gameplay, leveldesign
TGP1 Bug Database Team C27.14 | TGP1BC2714-2 | Dog Move towards cat on box entry | Bug | Done | Low | Done | Rui X. | Dominique S. | Dominique S. | 2017-11-07 11:59 |  | 2017-11-30 22:04 | 2017-11-08 10:03 |  | At times when a cat enters the box, dogs still move as if they still see the cat. - A cat will enter the box. - A dog will move with exclamatory mark with over their head. - Happens a lot on the last level "Mirrorz" | [5 empty] | Bugs, SD-Design, leveldesign
TGP1 Bug Database Team C27.14 | TGP1BC2714-3 | Dog Turning In The Direction of Which Cat It's Chasing | Task | Done | Medium | Done | Rui X. | Dominique S. | Dominique S. | 2017-11-07 12:10 |  | 2017-11-10 09:15 | 2017-11-10 09:15 |  | The dog doesn't turn in the direction of the cat it's chasing. - The dog doesn't turn from its default direction. | [5 empty] | animation, art, gameplay, leveldesign
TGP1 Bug Database Team C27.14 | TGP1BC2714-4 | Adding Sound To Make The World Feel Alive | Task | Done | Medium | Done | Dominique S. | Dominique S. | Dominique S. | 2017-11-07 12:27 | 2017-11-08 11:32 | 2017-11-08 11:34 | 2017-11-08 11:34 | 6300 | Add sound to make the game have more personality. - Win screen must feel more rewarding. - Cats and dogs need audio to their movement to convey living objects. - Cat Nip must play sound in order to make players feel rewarded for collecting them. | 100% | 100% | 6300 | 0 |  | audio, gameplay, leveldesign
TGP1 Bug Database Team C27.14 | TGP1BC2714-5 | Dogs Combining Onto One Node | Bug | To Do | Low | Unresolved | Unassigned | Dominique S. | Dominique S. | 2017-11-07 12:35 | 2017-12-01 09:57 | 2017-11-07 19:31 |  |  | On certain levels, dogs will come together and move as one piece. | [5 empty] | animation, gameplay, leveldesign
TGP1 Bug Database Team C27.14 | TGP1BC2714-6 | Number of turns in level 4 is incorrect | Bug | Done | Low | Done | Chris W. | Dominique S. | Dominique S. | 2017-11-08 09:48 | 2017-12-01 09:57 | 2017-11-08 09:49 | 2017-11-08 09:49 |  | The level should be beaten in 6 turns, not 12. | [5 empty] | LVL, leveldesign
TGP1 Bug Database Team C27.14 | TGP1BC2714-7 | Adding Particles To Make The Game Feel Rewarding | Task | Done | Medium | Done | Rui X. | Dominique S. | Dominique S. | 2017-11-08 10:45 |  | 2017-11-08 11:34 | 2017-11-08 11:34 |  | Add particles to make the game feel more rewarding for players. | [5 empty] | LVL, animation, leveldesign
TGP1 Bug Database Team C27.14 | TGP1BC2714-8 | Optimal Path needs to be updated. | Bug | Done | Medium | Done | Unassigned | Ashley P. | Ashley P. | 2017-11-08 11:33 | 2017-11-08 11:53 | 2017-11-08 12:23 | 2017-11-08 12:23 | 1800 | Some levels don't have the correct optimal path. Reword the levels to say "Completed in" before the optimal path | 100% | 100% | 1800 | 0
TGP1 Bug Database Team C27.14 | TGP1BC2714-9 | Dog ! and ? on butt instead of head when sprite flipped | Bug | Done | Medium | Done | Rui X. | Chris W. | Chris W. | 2017-11-09 11:45 |  | 2017-11-10 09:15 | 2017-11-10 09:15 |  | When we fixed the sprite flipping the ! and ? went on the dogs butt. | 0% | 0% |  | 3600 | 3600 | programming
TGP1 Bug Database Team C27.14 | TGP1BC2714-10 | Update optimal path for Tank Boi | Bug | Done | Medium | Done | Unassigned | Chris W. | Chris W. | 2017-11-10 09:14 |  | 2017-11-30 22:09 | 2017-11-10 11:18 |  |  | 0% | 0% |  | 1800 | 1800 | Acievements, Level
TGP1 Bug Database Team C27.14 | TGP1BC2714-11 | Tank Boi node is broken | Bug | Done | Highest | Done | Chris W. | Chris W. | Chris W. | 2017-11-10 10:53 |  | 2017-11-10 11:18 | 2017-11-10 11:18 |  | new added node is broked | 0% | 0% |  | 900 | 900 | Level
TGP1 Bug Database Team C27.14 | TGP1BC2714-12 | Tutorial text in level 3 is confusing some players | Bug | Done | Medium | Done | Rui X. | Chris W. | Chris W. | 2017-11-10 11:19 |  | 2017-11-15 12:05 | 2017-11-15 12:05 |  | Calling it just water is making people think that the leak is something that the cat can't pass through. we should think about fixing that | [5 empty] | level
TGP1 Bug Database Team C27.14 | TGP1BC2714-13 | Achievement system on level select screen doesn't display catnip collection | Bug | Done | Medium | Done | Rui X. | Ashley P. | Ashley P. | 2017-11-14 10:46 | 2017-11-15 10:32 | 2017-11-15 10:32 | 2017-11-15 10:32 | 1800 | The third paws on the level select screen don't show whether catnip is collected. | 100% | 100% | 1800 | 0 |  | programming
TGP1 Bug Database Team C27.14 | TGP1BC2714-14 | Fix Replay Button Color | Bug | To Do | Medium | Unresolved | Unassigned | Chris W. | Chris W. | 2017-11-14 10:55 |  | 2017-11-14 10:55 |  |  | People didn't seem to know the replay button was there. We should change the color on it. | 0% | 0% |  | 900 | 900
TGP1 Bug Database Team C27.14 | TGP1BC2714-15 | Redesign Level 2 so players have to enter and exit the box | Bug | Done | Medium | Done | Unassigned | Chris W. | Chris W. | 2017-11-14 10:55 |  | 2017-11-30 22:07 | 2017-11-15 12:01 |  | People don't understand the box, we should make level 2 clearer to know how the boxes work.
TGP1 Bug Database Team C27.14 | TGP1BC2714-16 | Achievement 'pop' only when a new achievement is achieved.unlocked | Bug | Done | Low | Done | Rui X. | Chris W. | Chris W. | 2017-11-14 11:01 | 2017-11-17 12:25 | 2017-11-30 22:08 | 2017-11-17 12:25 |  | Some people think the only time you get the 'pop' effect on a new achievements or the first time you get it.
TGP1 Bug Database Team C27.14 | TGP1BC2714-17 | Have the shader update on all cats when in line of sight of a dog | Bug | Done | High | Done | Rui X. | Chris W. | Chris W. | 2017-11-16 12:07 |  | 2017-11-30 22:08 | 2017-11-30 22:02 |  | Noticable easily in Hummer, the cat shader updates at the beginning of the dogs turn which sometimes makes the wrong cat red when they are moved in the path on adjacent nodes | 0% | 0% |  | 7200 | 7200 | programming
TGP1 Bug Database Team C27.14 | TGP1BC2714-18 | Turn counter increments during cat move if you tap the destination node repeatedly | Bug | To Do | Low | Unresolved | Unassigned | Ashley P. | Ashley P. | 2017-11-17 12:18 | 2017-12-01 09:57 | 2017-11-17 12:18
Generated at Fri Dec 01 09:58:08 CST 2017 by Ashley P. using JIRA 7.1.8#71012-sha1:d83491778ddf5df967f3c738fa396f8b341ab597.